## Sheet1
| Notes |  |  | PLAN AND REVIEW DEADLINE | ACG & BC OUT |  | PROJECT PLAN VIDEO |  |  |  |  | CHRISTMAS BREAK | CHRISTMAS BREAK | CHRISTMAS BREAK | CHRISTMAS BREAK |  | ACG & BC HAND IN | PROJECT DEMO | ACV, NLP & ACG OUT | [6 empty] | EASTER BREAK | EASTER BREAK | EASTER BREAK | EASTER BREAK | EASTER BREAK | FINAL, ACV HAND IN | ORAL; ACG & NLP HAND IN
| W/C | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01
Difficulty | Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Non-Project Tasks
N/A | ACG COURSEWORK I | bar: 4 to 16
N/A | BC COURSEWORK | bar: 4 to 16
N/A | ACV COURSEWORK | bar: 18 to 30
N/A | ACG COURSEWORK II | bar: 18 to 31
N/A | NLP COURSEWORK | bar: 18 to 31
N/A | EXAM REVISION | bar: 20 to 31
Project Tasks
Basic | Literature Review | bar: 1 to 3
Basic | Project Plan | bar: 1 to 3
Project Video | bar: 3 to 6
Basic | Project Video Plan | bar: 3
Basic | Project Video PowerPoint | bar: 3 to 4
Basic | Create Project Video | bar: 4 to 5
Basic | Review Project Video | bar: 4 to 6
Literature Implementations | bar: 2 to 11
Basic | Understand Existing Implementation Repos | bar: 2
Basic | Implement Finetuning | bar: 3
Basic | Implement Offline Training | bar: 3
Basic | Implement EWC | bar: 4
Intermediate | Implement GDumb | bar: 4
Intermediate | Implement Mnemonics | bar: 4 to 5
Intermediate | Implement Rainbow Memory | bar: 5 to 6
Intermediate | Implement FearNet | bar: 5 to 6
Advanced | Implement L2P | bar: 6 to 8
Advanced | Implement LNIDA | bar: 6 to 8
Basic | Review Potential Additional Solutions | bar: 8 to 9
Advanced | Allocated Time for Additional Implementations | bar: 8 to 11
Novel Implementation | bar: 6 to 17
Advanced | Preliminary Investigation of Potential Solutions | bar: 6 to 7
Advanced | Explain Theorectical Underpinning | bar: 8 to 10
Advanced | Implement Potential Solution | bar: 10 to 15
Advanced | Alllocated Time for Revising Solution Design | bar: 15 to 17
Evaluation | bar: 2 to 17
Basic | Methodology Planning | bar: 2 to 4
Basic | Existing Implementation Analysis and Comparison | bar: 5 to 8
Intermediate | Compare Novel Solution | bar: 14 to 17
Final Paper | bar: 3 to 24
Basic | Introduction Chapter | bar: 3 to 5
Basic | Methodology Chapter | bar: 4 to 7
Basic | Results / Evaluation Chapter | bar: 8 to 11; 16 to 18
Intermediate | Existing Implementation Chapter | bar: 5 to 13
Advanced | Novel Implementation Chapter | bar: 10 to 18
Basic | Conclusion Chapter | bar: 17 to 21
Basic | Completed First Draft | bar: 20 to 21
Basic | Review and Revise Paper | bar: 22 to 24
Oral Presentation | bar: 23 to 28
Basic | Presentation Plan | bar: 23 to 24
Basic | Presentation PowerPoint Draft | bar: 25 to 27
Basic | Review and Revise Presentation | bar: 27 to 28