## Sheet1
Difficulty | Deliverable | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Basic | Literature Review | bar: 1 to 3
Basic | Project Plan | bar: 1 to 3
Project Video | bar: 3 to 6
Basic | Project Video Plan | bar: 3
Basic | Project Video PowerPoint | bar: 3 to 4
Basic | Create Project Video | bar: 4 to 5
Basic | Review Project Video | bar: 4 to 6
Literature Implementations | bar: 2 to 11
Basic | Understand Existing Implementation Repos | bar: 2
Basic | Implement Finetuning | bar: 3
Basic | Implement Offline Training | bar: 3
Basic | Implement EWC | bar: 4
Basic | Implement iCaRL | bar: 4
Intermediate | Implement GDumb | bar: 4
Intermediate | Implement Mnemonics | bar: 4 to 5
Intermediate | Implement Rainbow Memory | bar: 5 to 6
Intermediate | Implement FearNet | bar: 5 to 6
Advanced | Implement L2P | bar: 6 to 8
Advanced | Implement LNIDA | bar: 6 to 8
Basic | Review Potential Additional Solutions | bar: 8 to 9
Advanced | Allocated Time for Additional Implementations | bar: 8 to 11
Novel Implementation | bar: 6 to 17
Advanced | Preliminary Investigation of Potential Solutions | bar: 6 to 7
Advanced | Explain Theorectical Underpinning | bar: 8 to 10
Advanced | Implement Potential Solution | bar: 10 to 15
Advanced | Alllocated Time for Revising Solution Design | bar: 15 to 17
Evaluation | bar: 2 to 17
Basic | Methodology Planning | bar: 2 to 4
Basic | Existing Implementation Analysis and Comparison | bar: 5 to 8
Intermediate | Compare Novel Solution | bar: 14 to 17
Final Paper | bar: 3 to 24
Basic | Introduction Chapter | bar: 3 to 5
Basic | Methodology Chapter | bar: 4 to 7
Basic | Results / Evaluation Chapter | bar: 8 to 11; 16 to 18
Intermediate | Existing Implementation Chapter | bar: 5 to 13
Advanced | Novel Implementation Chapter | bar: 10 to 18
Basic | Conclusion Chapter | bar: 17 to 21
Basic | Completed First Draft | bar: 20 to 21
Basic | Review and Revise Paper | bar: 22 to 24
Oral Presentation | bar: 23 to 28
Basic | Presentation Plan | bar: 23 to 24
Basic | Presentation PowerPoint Draft | bar: 25 to 27
Basic | Review and Revise Presentation | bar: 27 to 28